## Sheet1
		Project Estimation

Particulars			Time in hrs		Cost/hr		Total
Topic searching			8		100		800
Confirmation and finalisation of topic			2		50		100
Literature survey			10		200		2000
Finalizing objectives			4		100		400
Installation of required packages			2		100		200
Development of frontend			21		300		6300
Development of backend			30		300		9000
Linking of frontend and backend			6		200		1200
Manual testing of code			5		100		500

		Total	88			Total	20500

Calculation of efforts

Particulars				Days invested
Topic searching				5
Confirmation and finalisation of topic				1
Literature survey				6
Finalizing objectives				2
Installation of required packages				1
Development of frontend				9
Development of backend				12
Linking of frontend and backend				2
Manual testing of code				1
				39